## Dashboard
JCG Network TS Platform
Network Troubleshooting & Intelligence Platform
Developed by Manny Colón for JCG Solutions
CURRENT FOCUS | Foundation + RF Hardening | SPRINT | 1
STATUS | IN PROGRESS | BLOCKERS | 0
DO NOW
1 | Freeze/tag known-good RF build
2 | Finish JCG branding + vendor-neutral RF terminology
3 | Evidence Schema v1 + provenance/freshness
4 | RF parser fixtures + automated regression tests
5 | Packet Capture Engine
RULE | Evidence first. AI interprets evidence; it never invents evidence.
DEV REMINDER | npm run dev:restart

## Tasks
ID | Phase | Task | Priority | Status | Owner | Depends On | Done When
1 | Baseline | Freeze/tag known-good RF build | P0 | In Progress | Manny |  | Known-good RF build is tagged and reproducible
2 | Foundation | Complete JCG Network TS branding | P0 | In Progress | Manny | 1 | Visible UI uses JCG branding; MIT attribution retained
3 | Foundation | Remove obsolete macOS airport paths/dead code | P0 | Not Started | Manny | 1 | No legacy airport collector can overwrite evidence
4 | Foundation | Define Evidence Schema v1 | P0 | Not Started | Manny | 1 | Vendor-neutral schema documented and implemented
5 | Foundation | Add provenance, timestamp and freshness | P0 | Not Started | Manny | 4 | Every datum declares source/type/freshness
6 | RF Analyzer | Rename to Observed RF Environment | P0 | Not Started | Manny | 2 | No unsupported neighbor/interference language remains
7 | RF Analyzer | Channel width / overlap reasoning | P1 | Not Started | Manny | 4,6 | CCI/ACI candidates based on defensible RF evidence
8 | Quality | Create macOS RF fixtures | P0 | Not Started | Manny | 3 | Known system_profiler outputs stored as fixtures
9 | Quality | Automated RF parser regression tests | P0 | Not Started | Manny | 8 | CI fails on known parser regressions
10 | Packet | Fix packet capture lifecycle | P0 | Not Started | Manny | 4 | Capture starts/stops reliably with status/errors
11 | Packet | Deep packet analysis - DHCP/DNS/ARP/TCP/TLS | P0 | Not Started | Manny | 10 | Transactions reconstructed deterministically
12 | Evidence | Incident workspace + evidence store | P1 | Not Started | Manny | 4,5 | Incident ties RF, PCAP, API and findings together
13 | Meraki | Shared Meraki Evidence Service | P0 | Not Started | Manny | 4,5 | Caching/rate limit/retry/pagination centralized
14 | Meraki | Wireless evidence adapter | P0 | Not Started | Manny | 13 | Client/RF/roam/connectivity evidence normalized
15 | Meraki | Switching evidence adapter | P0 | Not Started | Manny | 13 | Ports/VLAN/STP/PoE/topology evidence normalized
16 | Meraki | MX Security expert evidence adapter | P0 | Not Started | Manny | 13 | MX routing/security/SD-WAN/VPN evidence normalized
17 | Path | Path Reconstruction Engine | P1 | Not Started | Manny | 14,15,16 | Expected traffic path is built and verified
18 | Palo Alto | PAN-OS/ Panorama evidence adapter | P1 | Not Started | Manny | 4,5 | Sessions/logs/policy/NAT/routing evidence normalized
19 | Cisco ISR | ISR920 evidence adapter | P1 | Not Started | Manny | 4,5 | Routes/interfaces/ARP/CEF/MAN evidence normalized
20 | Zscaler | ZIA evidence adapter | P1 | Not Started | Manny | 4,5 | Internet/SaaS secure-access evidence normalized
21 | Zscaler | ZPA evidence adapter | P1 | Not Started | Manny | 4,5 | Private-app path and connector evidence normalized
22 | Agents | Provider-neutral agent runtime | P1 | Not Started | Manny | 12-21 | Agents can use GPT/Claude/Ollama without domain rewrite
23 | Agents | Domain expert agents | P1 | Not Started | Manny | 22 | Wireless/routing/switching/DHCP/WAN/packet experts operational
24 | Agents | Vendor/security expert agents | P1 | Not Started | Manny | 22 | Meraki MX/Palo Alto/ZIA/ZPA/ISR experts operational
25 | RCA | RCA evidence correlation agent | P1 | Not Started | Manny | 23,24 | Ranked findings cite evidence and confidence
26 | Validation | Evidence Replay + known-failure library | P1 | Not Started | Manny | 25 | Agent versions benchmark against identical evidence
27 | Future | Catalyst managed switch adapter | P2 | Later | Manny | 4,5 | Catalyst evidence normalized without core redesign
28 | Production | Security/RBAC/secrets/audit | P1 | Later | Manny | 12 | Production readiness security gate passes
29 | Production | Standalone core / CLI / Web separation | P2 | Later | Manny | 4 | Diagnostic engine no longer depends on VS Code

## What I Need
When | Category | Need from Manny / Environment | Status | Notes
Now | Meraki | Confirm new platform can retrieve existing Meraki API credential securely; keep development read-only | Open | Do not paste API key into chat/source
Now | Development | Current Mac + VS Code + Node/npm + GitHub access | Ready | Already sufficient
Now | Packet tools | tcpdump availability; tshark/Wireshark when packet phase begins | Open | Run which tcpdump / which tshark
Soon | DCC Pilot | A few known test clients (especially Zebra scanners) and permission for read-only validation | Open | Use controlled test population
Soon | Palo Alto | Models, PAN-OS versions, Panorama coverage, permitted API methods | Open | Credentials later via secure storage
Soon | Cisco ISR | Exact ISR920 models, IOS/IOS-XE versions, management method, SSH/NETCONF/RESTCONF/SNMP availability | Open | No credentials yet
Soon | Zscaler | ZIA/ZPA tenant architecture, API availability, Client Connector/log access, App Connector inventory | Open | No credentials yet
Later | Hardware | Optional external Wi-Fi capture adapter / dedicated Linux JCG Probe | Later | Not required for current build
Later | Production | Secrets manager, PostgreSQL, container host, RBAC/auth design | Later | Before production deployment

## Roadmap
Stage | Focus | Outcome / Gate
Sprint 1 | Foundation + RF Hardening | G1: Local evidence independently validated
Sprint 2 | RF Intelligence + Packet Capture | Reliable RF reasoning and capture lifecycle
Sprint 3 | Deep Packet Analysis | Deterministic protocol transaction reconstruction
Sprint 4 | Meraki Evidence Platform | G2: Vendor evidence matches Dashboard/device evidence
Sprint 5 | DCC Pilot | Real incident validation against engineer conclusions
Sprint 6 | Palo Alto + ISR | Firewall and MAN path evidence
Sprint 7 | Zscaler ZIA/ZPA | Secure-access path evidence
Sprint 8 | Path Reconstruction | End-to-end expected path verification
Sprint 9 | Agent Framework | Specialist agents use approved evidence/tools
Sprint 10 | RCA + Disagreement | G4: Multi-agent findings cite evidence/confidence
Later | Catalyst + Productionization | G5: Production security/readiness